## Gantt Chart Template
GANTT CHART | [27 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | APLICATIVO WEB IKERNELL |  |  |  |  | COMPANY NAME | [8 empty] | SENA
| PROJECT MANAGER | DIEGO BOADA |  |  |  |  | DATE | [8 empty] | 2026-06-05
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | DOCUMENTACIÓN
1,1 | Documento Historias de usuario | Efrain M. | 2026-06-05 | 2026-06-09 | 4 | 100% | bar: WEEK 1 5 F to WEEK 2 9 T
1,2 | Documento Requerimientos funcionales y no funcionales | Efrain M. | 2026-06-05 | 2026-06-09 | 4 | 100% | bar: WEEK 1 5 F to WEEK 2 9 T
1,3 | Documento Casos de uso | Efrain M. | 2026-06-09 | 2026-06-10 | 1 | 90% | bar: WEEK 2 9 T to WEEK 2 10 W
1,4 | Diagramas UML | Efrain M. | 2026-06-09 | 2026-06-10 | 1 | 100% | bar: WEEK 2 9 T to WEEK 2 10 W
1,5 | Modelo entidad-relación | Efrain M. | 2026-06-11 | 2026-06-11 | 0 | 100% | bar: WEEK 2 11 R
2 | BASE DE DATOS
2,1 | Diseño PostgreSQL | Efrain M. | 2026-06-11 | 2026-06-12 | 1 | 100% | bar: WEEK 2 11 R to WEEK 2 12 F
2,2 | Scripts DDL | Efrain M. | 2026-06-11 | 2026-06-12 | 1 | 100% | bar: WEEK 2 11 R to WEEK 2 12 F
2,3 | Scripts DML | Efrain M. | 2026-06-11 | 2026-06-12 | 1 | 100% | bar: WEEK 2 11 R to WEEK 2 12 F
2,3 | Pruebas de base de datos | Efrain M. | 2026-06-11 | 2026-06-12 | 1 | 100% | bar: WEEK 2 11 R to WEEK 2 12 F
2,3 | Backup (.sql) | Efrain M. | 2026-06-25 | 2026-06-25 | 0 | 100% | bar: WEEK 4 25 R
3 | BACKEND SPRING BOOT
3,1 | Entidades JPA | Efrain M. | 2026-06-15 | 2026-06-17 | 2 | 100% | bar: WEEK 3 15 M to WEEK 3 17 W
3,2 | Repositorios | Efrain M. | 2026-06-15 | 2026-06-17 | 2 | 100% | bar: WEEK 3 15 M to WEEK 3 17 W
3,3 | Servicios | Efrain M. | 2026-06-15 | 2026-06-17 | 2 | 100% | bar: WEEK 3 15 M to WEEK 3 17 W
3,4 | Controladores REST | Efrain M. | 2026-06-16 | 2026-06-17 | 1 | 100% | bar: WEEK 3 15 M to WEEK 3 17 W
3,5 | Validaciones de negocio | Efrain M. | 2026-06-16 | 2026-06-25 | 9 | 60% | bar: WEEK 3 16 T to WEEK 4 25 R
3,6 | Login | Efrain M. | 2026-06-23 | 2026-06-23 | 0 | 100% | bar: WEEK 4 23 T
3,7 | Hash BCrypt | Efrain M. | 2026-06-23 | 2026-06-24 | 1 | 100% | bar: WEEK 4 23 T to WEEK 4 24 W
3,8 | Configuración CORS | Efrain M. | 2026-06-24 | 2026-06-25 | 1 | 80% | bar: WEEK 4 23 T to WEEK 4 25 R
4 | FRONTEND REACT
4,1 | Configuración proyecto React + Vite | Efrain M. | 2026-06-17 | 2026-06-25 | 8 | 99% | bar: WEEK 3 17 W to WEEK 4 25 R
4,2 | Landing Page | Efrain M. | 2026-06-17 | 2026-06-25 | 8 | 99% | bar: WEEK 3 17 W to WEEK 4 25 R
4,3 | Sistema de Login | Efrain M. | 2026-06-17 | 2026-06-25 | 8 | 99% | bar: WEEK 3 17 W to WEEK 4 25 R
4,4 | Dashboard | Efrain M. | 2026-06-17 | 2026-06-25 | 8 | 99% | bar: WEEK 3 17 W to WEEK 4 25 R
4,5 | CRUD Proyectos | Efrain M. | 2026-06-17 | 2026-06-25 | 8 | 99% | bar: WEEK 3 17 W to WEEK 4 25 R
4,6 | CRUD Usuarios | Efrain M. | 2026-06-17 | 2026-06-25 | 8 | 99% | bar: WEEK 3 17 W to WEEK 4 25 R
4,7 | CRUD Actividades | Efrain M. | 2026-06-17 | 2026-06-25 | 8 | 99% | bar: WEEK 3 17 W to WEEK 4 25 R
4,8 | CRUD Errores | Efrain M. | 2026-06-17 | 2026-06-25 | 8 | 99% | bar: WEEK 3 17 W to WEEK 4 25 R
4,9 | CRUD Interrupciones | Efrain M. | 2026-06-17 | 2026-06-25 | 8 | 99% | bar: WEEK 3 17 W to WEEK 4 25 R
4,10 | Gestión de Roles | Efrain M. | 2026-06-17 | 2026-06-25 | 8 | 85% | bar: WEEK 3 17 W to WEEK 4 25 R
4,11 | Perfil de usuario | Efrain M. | 2026-06-17 | 2026-06-25 | 8 | 99% | bar: WEEK 3 17 W to WEEK 4 25 R
5 | INTEGRACIÓN
5,1 | Integración Frontend-Backend | Efrain M. | 2026-06-17 | 2026-06-19 | 2 | 100% | bar: WEEK 3 17 W to WEEK 3 19 F
5,2 | Consumo de API REST | Efrain M. | 2026-06-17 | 2026-06-19 | 2 | 100% | bar: WEEK 3 17 W to WEEK 3 19 F
5,3 | Navegación protegida | Efrain M. | 2026-06-23 | 2026-06-25 | 2 | 70% | bar: WEEK 4 24 W to WEEK 4 25 R
6 | ENTREGA
4,3 | Corrección de errores | Efrain M. | 2026-06-23 | 2026-06-25 | 2 | 50% | bar: WEEK 4 23 T to WEEK 4 25 R
4,3 | README | Efrain M. | 2026-06-25 | 2026-06-25 | 0 | 50% | bar: WEEK 4 25 R
4,3 | GitHub | Efrain M. | 2026-06-05 | 2026-06-25 | 20 | 50% | bar: WEEK 1 5 F to WEEK 4 25 R
4,3 | Documentación Drive | Efrain M. | 2026-06-05 | 2026-06-12 | 7 | 50% | bar: WEEK 1 5 F to WEEK 2 12 F
4,3 | Entrega final | Efrain M. | 2026-06-25 | 2026-06-25 | 0 | 50% | bar: WEEK 4 25 R